## Sheet1
			16.3
Status	Item	Type	Estimate	Actual	Notes
DONE	Balsamiq Setup	Setup	0.3	0.5
DONE	City Overview Screen	Mockup	1.5	1
DONE	City Map Screen	Mockup	1	0.75
DONE	Neighbourhood Interaction Screen	Mockup	2	1.5
DONE	Castle Interaction Screen	Mockup	2	0.75	comped out, leads to out of scope gameplay
DONE	Upgrade Confirmation	Mockup	0.5	0.66
PROG	Balsamiq Project Refactor	Mockup	2		Update to Balsamiq project format; reconnect images
PROG	Core Loop Refactor	Documentation	1	1
	Resource Node	Documentation	1
	City Overview	Documentation	1
	Neighbourhood Overview	Documentation	1
	System Architecture I	Documentation	3