## Sheet1
			13.8
Status	Item	Type	Estimate	Actual
DONE	Balsamiq Setup	Setup	0.3	0.5
DONE	City Overview Screen	Mockup	1.5	1
DONE	City Map Screen	Mockup	1	0.75
	Neighbourhood Interaction Screen	Mockup	2
	Castle Interaction Screen	Mockup	2
	Core Loop Refactor	Documentation	1
	Resource Node	Documentation	1
	City Overview	Documentation	1
	Neighbourhood Overview	Documentation	1
	System Architecture I	Documentation	3